## Project tasks
Project name | Project Management
Project manager | Maged Monir Melek
Project start date | 2022-11-04 09:00
Project finish date | 2022-11-30 17:00
Duration | 19 days
% complete | 0%
Exported on | 2022-11-04 13:22
Task number | Outline number | Name | Duration | Start | Finish | Depends on | % complete | Bucket | Dependents (after) | Effort | Effort completed | Effort remaining | Assigned to
1 | 1 | TASK A | 3 days | 2022-11-04 09:00 | 2022-11-08 17:00 |  | 0% | Initiating | 2 - TASK B, 3 - TASK C
2 | 2 | TASK B | 4 days | 2022-11-09 09:00 | 2022-11-14 17:00 | 1 - TASK A | 0% | Initiating | 4 - TASK D
3 | 3 | TASK C | 2 days | 2022-11-09 09:00 | 2022-11-10 17:00 | 1 - TASK A | 0% | Initiating | 5 - TASK E, 6 - TASK F
4 | 4 | TASK D | 5 days | 2022-11-15 09:00 | 2022-11-21 17:00 | 2 - TASK B | 0% | Initiating | 7 - TASK G
5 | 5 | TASK E | 1 day | 2022-11-11 09:00 | 2022-11-11 17:00 | 3 - TASK C | 0% | Initiating | 7 - TASK G
6 | 6 | TASK F | 2 days | 2022-11-11 09:00 | 2022-11-14 17:00 | 3 - TASK C | 0% | Initiating | 8 - TASK H
7 | 7 | TASK G | 4 days | 2022-11-22 09:00 | 2022-11-25 17:00 | 4 - TASK D, 5 - TASK E | 0% | Initiating | 8 - TASK H
8 | 8 | TASK H | 3 days | 2022-11-28 09:00 | 2022-11-30 17:00 | 6 - TASK F, 7 - TASK G | 0% | Initiating